## Sheet1
Performance in Initiating Clinical Research (70 day Benchmark from site selected to first recruit consent)
2017/18 Quarter 4
* Report updated on the 29/05/2018 to include the "date site ready to start" column which had been omitted from the initial publicaiton | [13 empty] | Reasons for Failing the 70 day benchmark
Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Benchmark Met | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Reasons for delay correspond to:
16/YH/0489 | 197733 | HRA Approval | A randomized, multicenter STudy to evaluate the Effect of secukinumab 300 mg s.c. administered during 52 weeks to patients suffering from new-onset moderate to severe plaque Psoriasis as early Intervention compared to standard treatment with narrow band UVB (STEPIn study) | No |  | No | 2016-01-19 | 2017-06-02 | 2017-02-02 | 2017-07-06 | 2017-07-04 |  | 2017-07-04 | [6 empty] | Y |  |  |  | Neither
16/EM/0332 | 205699 | HRA Approval | MAXIMISE (Managing AXIal Manifestations in Psoriatic Arthritis with SEcukinumab), a randomized, double-blind, placebo-controlled, multicenter, 52 week study to assess the efficacy and safety of secukinumab 150 mg or 300 mg s.c. in patients with active psoriatic arthritis and axial skeleton involvement who have inadequate response to non steroidal anti-inflammatory drugs (NSAIDs) | Yes | 2017-06-08 | Yes | 2016-08-10 | 2017-04-10 | 2016-10-07 | 2017-04-04 | 2017-04-21 |  | 2017-05-17
16/NW/0726 | 213429 | HRA Approval | A double-blind, randomised, placebo-controlled study to assess the effect of SNF472 on progression of cardiovascular calcification on top of standard of care in end-stage-renal-disease (ESRD) patients on haemodialysis (HD) | Yes | 2017-05-17 | Yes | 2016-11-30 | 2017-04-10 | 2016-11-29 | 2017-04-14 | 2017-04-25 |  | 2017-04-25
17/NW/0035 | 209920 | HRA Approval | A study to evaluate the acceptability of a new phenylalanine free infant formula for use in the dietary management of Phenylketonuria in infants from birth to 2 year of age with regard to product tolerance and adherence. | Yes | 2017-07-13 | No | 2017-03-03 | 2017-04-12 | 2017-01-31 | 2017-04-10 | 2017-04-20 |  | 2017-04-20 | [8 empty] | Y |  | Neither
15/NS/0113 | 188563 | HRA Approval | The clinical and cost effectiveness of surgical interventions for stones in the lower kidney: The PUrE RCTPercutaneous Nephrolithotomy (PNL), Flexible Ureterorenoscopy (FURS) and Extracorporeal Lithotripsy (ESWL) for lower pole Kidney stones. | Yes | 2017-07-25 | Yes | 2017-03-15 | 2017-06-07 | 2017-06-09 | 2017-06-07 | 2017-06-22 |  | 2017-07-13
17/NE/0027 | 215796 | HRA Approval | CReST 2 - Colorectal Endoscopic Stenting Trial 2 | Yes | 2017-06-29 | Yes | 2017-04-20 | 2017-04-20 | 2017-04-03 | 2017-04-20 | 2017-05-31 |  | 2017-06-26
17/LO/0504 | 224298 | HRA Approval | An open-label, single arm, repeat dose, multi-centre study to evaluate the use of an autoinjector for the subcutaneous administration of mepolizumab in subjects with severe eosinophilic asthma (study 204959) | Yes | 2017-08-03 | Yes | 2017-04-28 | 2017-06-08 | 2017-05-15 | 2017-06-22 | 2017-07-05 |  | 2017-07-06
16/LO/0857 | 187133 | HRA Approval | Lugol?s Iodine in Surgical Treatment of Epithelial Dysplasia in the Oral Cavity and Oropharynx (LISTER) | Yes | 2017-10-03 | No | 2017-04-27 | 2017-05-30 | 2016-10-13 | 2017-05-30 | 2016-06-12 |  | 2017-06-12 | [5 empty] | Y |  |  |  |  | Neither
17/NW/0223 | 219119 | HRA Approval | A study to evaluate the acceptability of PKU explore, a renovated phenylalanine free second stage protein substitute for | Yes | 2017-07-20 | Yes | 2017-05-24 | 2017-05-24 | 2017-04-22 | 2017-06-19 | 2017-06-20 |  | 2017-06-20
16/NW/0396 | 191940 | HRA Approval | Mindex: The efficacy and safety of very low dose dexamethasone used to facilitate the extubation of ventilator dependent preterm babies who are at high risk of bronchopulmonary dysplasia | Yes | 2017-09-08 | Yes | 2016-04-14 | 2017-07-28 | 2016-06-30 | 2017-07-28 | 2017-08-08 |  | 2017-08-15
17/WA/0203 | 229705 | HRA Approval | A 12-week, single-blind, prospective, randomized, controlled, pilot clinical trial to evaluate surface area reduction with use of the MolecuLight i:X? Imaging Device compared to standard treatment of chronic wounds | Yes | 2017-07-25 | Yes | 2017-07-19 | 2017-07-19 | 2017-07-14 | 2017-07-19 | 2017-07-21 |  | 2017-07-25
16/WS/0154 | 205571 | HRA Approval | Does Occupational Therapist led home environmental assessment and modification reduce falls among high risk older people? | No |  | No | 2017-03-03 | 2017-04-19 | 2016-09-08 | 2017-04-19 | 2017-05-10 | [5 empty] | Y | Y |  |  | Y |  |  | Both
17/LO/0794 | 223700 | HRA Approval | A 52-Week Multicenter, Randomized, Open-Label, Parallel-Group Study Evaluating the Efficacy and Safety of Ixekizumab versus Adalimumab in Patients with Psoriatic Arthritis who are Biologic Disease-Modifying Anti-Rheumatic Drug Naive | No |  | No | 2017-05-12 | 2017-08-09 | 2017-07-28 | 2017-09-12 | 2017-09-13 |  | 2017-10-12 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
16/NI/0145 | 207927 | HRA Approval | Diode Subthreshold Micropulse Laser (DIAMONDS): A pragmatic, multicentre, allocation concealed, prospective, randomised, non-inferiority double-masked trial | Yes | 2017-11-30 | Yes | 2017-09-15 | 2017-09-21 | 2016-11-29 | 2017-09-21 | 2017-10-02 |  | 2017-10-19
17/YH/0097 | 221010 | HRA Approval | HERO Individually randomised controlled multi-centre trial to determine the clinical and cost effectiveness of a home-based exercise intervention for older people with frailty as extended rehabilitation following acute illness or injury, including embedded process evaluation | Yes | 2017-12-05 | No | 2017-07-11 | 2017-09-21 | 2017-06-25 | 2017-09-21 | 2017-10-12 |  | 2017-12-01 | [9 empty] | Y | Neither
16/YH/0463 | 185443 | HRA Approval | CAD/CAM nitinol bonded retainer versus a chairside bonded retainer: A multicenter randomised controlled trial. | Yes | 2018-03-28 | No | 2017-01-31 | 2017-11-14 | 2017-05-19 | 2017-11-14 | 2017-11-28 |  | 2017-11-28 | [5 empty] | Y |  |  |  |  | Neither
17/WS/0165 | 226413 | HRA Approval | A Single Arm, Open Label, Multicenter Study to Evaluate the Efficacy and Safety of Glecaprevir(GLE)/Pibrentasvir(PIB) in Treatment Na?ve Adults with Chronic Hepatitis C Virus (HCV) Genotypes 1 ? 6 Infection and Aspartate aminotransferase to Platelet Ratio Index (APRI) = 1 | Yes | 2017-12-20 | No | 2017-04-21 | 2017-09-22 | 2017-09-19 | 2017-11-13 | 2017-11-17 |  | 2017-11-28 | [5 empty] | Y |  | Y |  |  | Both
16/NS/0106 | 212541 | HRA Approval | RAACENO Reducing Asthma Attacks in Children using Exhaled Nitric Oxide | Yes | 2018-01-05 | Yes | 2017-05-03 | 2017-11-06 | 2017-04-04 | 2017-11-06 | 2017-11-23 |  | 2017-11-24
17/LO/1461 | 230430 | HRA Approval | A Phase IIB, randomised, observer-blind, placebo-controlled, multi-centre study to evaluate the efficacy, safety, reactogenicity and immunogenicity of the GSK Biologicals? investigational vaccine GSK3277511A when administered intramuscularly according to a 0, 2 months schedule in COPD patients aged 40 to 80 years with a previous history of acute exacerbation (AECOPD) | Yes | 2017-11-27 | Yes | 2017-06-02 | 2017-10-12 | 2017-10-10 | 2017-11-17 | 2017-11-20 |  | 2017-11-27
17/EM/0293 | 229955 | HRA Approval | A Multicenter, Randomized, Double-blind, Parallel Group, Placebo-controlled, Phase 3b Study to Evaluate the Safety and Efficacy of Benralizumab 30 mg sc in Patients with Severe Asthma Uncontrolled on Standard of Care Treatment (D3250C00045) | Yes | 2017-11-23 | Yes | 2017-07-25 | 2017-10-05 | 2017-09-22 | 2017-11-13 | 2017-11-13 |  | 2017-11-13
17/NW/0501 | 226463 | HRA Approval | Determinants of quality of life in dialysis patients and their carers | Yes | 2018-01-04 | Yes | 2017-10-17 | 2017-11-13 | 2017-10-12 | 2017-11-13 | 2017-12-07 |  | 2017-12-11
17/NW/0369 | 225797 | HRA Approval | PHASE III, DOUBLE-BLIND, PLACEBO-CONTROLLED, MULTICENTER, RANDOMIZED STUDY OF PRACINOSTAT IN combination with Azacitidine in Adult AML | No |  | No | 2017-06-20 | 2017-09-21 | 2017-09-15 | 2018-01-12 | 2018-01-22 | [6 empty] | Y |  |  | Y |  |  | Both
17/LO/0933 | 220629 | HRA Approval | SAPPHIRE: A randomized, masked, controlled trial to study the safety and efficacy of suprachoroidal CLS-TA in conjunction with intravitreal aflibercept in subjects with retinal vein occlusion | No |  | Within 70 Days | 2017-07-13 | 2018-03-20 | 2018-01-15 | 2018-04-04 | 2018-04-05
17/NE/0239 | 222301 | HRA Approval | Nasal Airway Obstruction Study | No |  | No | 2017-08-11 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2018-02-16 | [6 empty] | Y |  |  | Y |  |  | NHS Provider
17/YH/0269 | 228372 | HRA Approval | A Prospective, Open, Non-Comparative Multicentre Study to Evaluate a Fibrous Silver Dressing (DURAFIBER? Ag) in the Treatment of Moderate to Highly Exuding Venous Leg Ulcers | No |  | No | 2017-08-25 | 2017-09-21 | 2017-08-25 | 2018-02-09 | 2018-02-07 |  | 2018-02-19 | [7 empty] | Y |  |  | Sponsor
16/LO/1318 | 187932 | HRA Approval | Nucleos(t)ide withdrawal in HBeAg negative hepatitis B virus infection to promote HBsAg clearance. (NUC-B) | No |  | Within 70 Days | 2017-10-17 | 2018-02-21 | 2016-09-21 | 2018-02-21 | 2018-02-23
17/LO/0962 | 220190 | HRA Approval | Helping Pregnant smokers quit: A multi-centre RCT of electronic cigarettes and nicotine patches | Yes | 2018-02-26 | Yes | 2017-08-11 | 2017-12-21 | 2017-07-24 | 2017-12-18 | 2018-02-02 |  | 2018-02-06
17/SC/0391 | 227067 | HRA Approval | The High-volume Haemodiafiltration vs High-flux Haemodialysis Registry Trial | Yes | 2018-02-16 | Yes | 2017-11-08 | 2017-12-21 | 2017-09-07 | 2017-12-21 | 2018-02-06 |  | 2018-02-07
17/EE/0361 | 231209 | HRA Approval | A 2-treatment period, randomised, placebo-controlled, multicentre parallel-group study to assess the safety of QAW039 when added to existing asthma therapy in GINA steps 3, 4 and 5 patients with uncontrolled asthma. | Yes | 2018-02-15 | Yes | 2017-12-14 | 2018-02-06 | 2017-10-31 | 2018-02-02 | 2018-02-06 |  | 2018-02-14
Note on N4: Format dd/mm/yyyy.