## Sheet1
Performance in Initiating Clinical Research
Q2 2019/20 Submission
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Reasons for delay correspond to:
18/YH/0017 | 231431 | ISCOMAT Work Package 4 | Yes | 2019-03-18 | 2017-11-22 | 2018-10-31 | 2018-03-01 | 2018-10-31 | 2018-12-04 | 2019-02-21 |  |  |  | Y | [6 empty] | Sponsor
17/YH/0392 | 230501 | A randomized, double-masked, placebo-controlled exploratory study to evaluate safety, tolerability, pharmacodynamics and pharmacokinetics of orally administered BI 1467335 for 12 weeks with a 12 week follow up period in patients with non proliferative diabetic retinopathy without centre-involved diabetic macular edema. | Yes | 2019-04-25 | 2018-11-12 | 2018-11-12 | 2018-01-26 | 2018-10-23 | 2018-11-23 | 2018-12-07 | [5 empty] | Y |  |  |  |  | Neither
18/LO/1110 | 248048 | A Phase 3 randomised, double-blind, active-controlled, parallel-group, multi-center study in haemodialysis participants with anaemia of chronic kidney disease to evaluate the efficacy, safety and pharmacokinetics of threetimes weekly dosing of daprodustat compared to recombinant human erythropoietin, following a switch from recombinant human erythropoietin or its analogs. | No |  | 2018-07-02 | 2018-10-03 | 2018-07-25 | 2018-10-09 | 2018-10-15 | 2018-10-16 | [5 empty] | Y |  |  |  |  | Neither
18/LO/1311 | 248599 | A PHASE III, MULTICENTER, RANDOMIZED, DOUBLE-MASKED, ACTIVE COMPARATOR?CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF RO6867461 IN PATIENTS WITH DIABETIC MACULAR EDEMA (RHINE) | Yes | 2018-11-01 | 2018-07-06 | 2018-10-04 | 2018-10-03 | 2018-10-04 | 2018-10-09 | 2018-10-11
17/LO/1509 | 232288 | MS-STAT2 A phase 3 randomised, double blind, clinical trial investigating the effectiveness of repurposed simvastatin compared to placebo, in secondary progressive multiple sclerosis, in slowing the progression of disability | Yes | 2019-01-23 | 2018-10-12 | 2018-10-21 | 2018-01-16 | 2018-10-21 | 2018-11-30 | 2018-11-30 | [5 empty] | Y |  |  |  |  | Neither
18/EE/0378 | 248600 | A Multicenter, Double-Masked, Randomized, Dose-Ranging Trial to Evaluate the Efficacy and Safety of Conbercept Intravitreal Injection in Subjects with Neovascular Age-related Macular Degeneration | Yes | 2019-07-23 | 2018-07-23 | 2019-05-01 | 2019-01-09 | 2019-05-02 | 2019-05-07 | 2019-05-30 | [6 empty] | Y |  |  |  | Neither
18/SC/0243 | 240684 | HPS-4/TIMI 65/ORION-4: A double-blind randomized placebo-controlled trial assessing the effects of inclisiran on clinical outcomes among people with atherosclerotic cardiovascular disease | Yes | 43578 | 2018-02-16 | 2018-12-20 | 2018-10-01 | 2018-12-20 | 2019-01-28 | 2019-04-08 | Y | [9 empty] | NHS Provider
17/EM/0288 | 222668 | A randomised feasibility trial to define outcome measures for acute Charcot neuroarthropathy in Diabetes and their use in assessing clinical management. | Yes | 43600 | 2018-10-23 | 2019-01-16 | 2018-10-04 | 2019-01-16 | 2019-02-20 | 2019-04-17 |  |  |  |  | Y |  |  | Y |  |  | Both
18/YH/0392 | 252761 | A Phase 2b, randomized, double-blind, placebo-controlled, dose-ranging, multi-center study to evaluate the efficacy and safety of GB001 as maintenance therapy in adult subjects with moderate to severe asthma | Yes | 2019-03-25 | 2018-06-11 | 2018-11-19 | 2018-11-15 | 2019-02-07 | 2019-02-12 | 2019-03-05 | Y |  |  |  |  | Y |  | Y |  |  | Sponsor
17/SC/0406 | 217627 | The COMET Trial: Concordance between MRI and Pathology in the Diagnosis of Extranodal Tumour Deposits | No |  | 2018-11-07 | 2018-11-08 | 2018-10-05 | 2019-11-08 | 2019-02-12 | [5 empty] | Y |  |  | Y |  |  | Both
17/EE/0307 | 229942 | A trial comparing the effect and safety of insulin degludec versus insulin detemir, both in combination with insulin aspart, in the treatment of pregnant women with type 1 diabetes. | Yes | 2019-05-09 | 2019-02-07 | 2019-02-07 | 2017-09-21 | 2019-02-21 | 2019-02-22 | 2019-04-01 |  |  |  | Y | Y | Y |  |  |  |  | Both
18/YH/0443 | 252415 | A 52-week, multicenter, randomized, double-blind, double-dummy, parallel-group, placebo-controlled study of fevipiprant once daily plus standard-of-care (SoC) for reduction of systemic corticosteroids (oral and parenteral) use in patients with severe asthma | Yes | 43567 | 2018-11-15 | 2019-02-28 | 2018-12-10 | 2019-03-07 | 2019-03-13 | 2019-03-27 |  |  |  | Y | [6 empty] | Sponsor
18/NW/0813 | 256738 | A randomized, double-blind, multicenter study assessing short (16 weeks) and long-term efficacy (up to 1 year), safety, and tolerability of 2 subcutaneous secukinumab dose regimens in adult patients with moderate to severe hidradenitis suppurativa | Yes | 2019-05-16 | 2019-01-23 | 2019-01-23 | 2019-01-16 | 2019-02-26 | 2019-02-26 | 2019-03-12 |  |  |  |  | Y | [5 empty] | NHS Provider
18/SC/0222 | 223737 | NeoCLEAR: Neonatal Champagne Lumbar punctures Every time ? An RCT. A multicentre, randomised controlled 2x2 factorial trial to investigate techniques to increase lumbar puncture success | Yes | 2019-02-26 | 2018-12-28 | 2019-01-15 | 2018-06-12 | 2019-01-15 | 2019-02-07 | 2019-02-26
18/NE/0296 | 248487 | CArvediloL versus variceal Band ligation in primary pREvention of variceal bleeding in liver cirrhosis | Yes | 2019-05-02 | 2019-01-24 | 2019-03-14 | 2018-10-19 | 2019-03-14 | 2019-04-01 | 2019-04-01
18/YH/0380 | 249030 | Multi-Morbidity in Older Adults with Depression (MODS): Work Stream 1 (WS1) | Yes | 43614 | 2019-01-28 | 2019-02-14 | 2018-11-13 | 2019-02-14 | 2019-02-26 | 2019-04-15 |  |  |  | Y |  |  | Y |  |  |  | Sponsor
19/YH/0124 | 253681 | A cluster randomised trial to evaluate the effect of a school-based intervention to improve academic achievement, visual acuity, and adherence to glasses wear, in young children in a disadvantaged multi-ethnic community. | Yes | 2019-09-16 | 2019-05-08 | 2019-05-13 | 2019-05-07 | 2019-05-13 | 2019-06-07 | 2019-09-16
17/SC/0070 | 215616 | The Prepare Multi-Morbid Older People for End-stage Kidney Disease Trial | Yes | 2019-07-31 | 2018-11-07 | 2019-05-10 | 2017-05-30 | 2019-05-10 | 2019-06-20 | 2019-06-20 |  |  |  |  | Y | Y |  |  |  |  | NHS Provider
18/WM/0383 | 252607 | A phase 3 study investigating the efficacy, safety, and tolerability of tralokinumab administered to adult subjects with severe atopic dermatitis who are not adequately controlled with or have contraindications to oral cyclosporine A. | Yes - Date Unavailable |  | 2018-11-27 | 2019-04-05 | 2019-02-06 | 2019-04-09 | 2019-04-11 | 2019-06-13 |  |  |  |  | Y |  | Y |  |  |  | NHS Provider
18/YH/0358 | 242342 | A randomised controlled trial to establish the clinical and cost effectiveness of expectant management versus preoperative imaging with Magnetic Resonance Cholangiopancreatography (MRCP) in patients with symptomatic gallstones undergoing laparoscopic cholecystectomy at low or moderate risk of common bile duct stones | Yes | 2019-06-26 | 2019-01-29 | 2019-04-24 | 2018-12-12 | 2019-04-24 | 2019-05-08 | 2019-06-03 |  |  |  | Y | Y | [5 empty] | Both
19/EM/0047 | 257111 | A PHASE III, MULTICENTER, RANDOMIZED, DOUBLE-MASKED, ACTIVE COMPARATOR-CONTROLLED STUDY TO EVALUATE THE EFFICACY AND SAFETY OF FARICIMAB IN PATIENTS WITH NEOVASCULAR AGE-RELATED MACULAR DEGENERATION (TENAYA) | Yes | 2019-04-23 | 2019-02-06 | 2019-04-05 | 2019-04-04 | 2019-04-05 | 2019-04-10 | 2019-04-11
19/EM/0112 | 259565 | A multi-center, proof-of-mechanism study of multiple, oral doses of fevipiprant (QAW039) in COPD patients with eosinophilia | Yes | 2019-08-07 | 2019-02-20 | 2019-05-28 | 2019-05-21 | 2019-06-07 | 2019-06-10 | 2019-06-12
18/LO/2033 | 252294 | When to Induce Labour to Limit risk in pregnancy hypertension ? a multicentre, randomised controlled trial | No |  | 2019-02-28 | 2019-06-13 | 2019-01-10 | 2019-06-13 | 2019-06-27 | 2019-06-28 | [5 empty] | Y | Y |  |  |  | Neither
18/WM/0070 | 236540 | The Impact of Sleep Disorders in Patients with Type 2 Diabetes: A Cohort Study and Feasibility RCT | Yes | 2019-07-03 | 2019-03-11 | 2019-04-02 | 2018-05-24 | 2019-05-13 | 2019-05-23 | 2019-06-25 |  |  |  | Y | [6 empty] | Sponsor
19/NW/0158 | 259931 | SCIENCE Surgery or Cast for Injuries of the EpicoNdyle in Children?s Elbows:A multi-centre prospective randomised superiority trial of operative fixation versus non-operative treatment for medial epicondyle fractures of the humerus in children. | Yes | 2019-09-23 | 2019-03-27 | 2019-05-14 | 2019-03-25 | 2019-05-29 | 2019-05-30 | 2019-06-03 | [8 empty] | Y |  | Neither
19/EM/0110 | 260251 | Efficacy and Safety of Brolucizumab versus Aflibercept in Adult Patients with Visual Impairment due to Macular Oedema secondary to Branch Retinal Vein Occlusion (RAPTOR) | No |  | 2019-04-01 | 2019-05-22 | 2019-05-21 | 2019-06-06 | 2019-06-10 | 2019-08-07 |  |  |  | Y |  | Y |  |  |  |  | Sponsor
19/NW/0360 | 251301 | NG-Sure WP2 Sampling Feasibility Study | Yes | 2019-08-27 | 2019-06-20 | 2019-06-20 | 2019-06-19 | 2019-06-20 | 2019-08-02 | 2019-08-15 | Y | [9 empty] | NHS Provider
18/LO/02111 | 254025 | Quality-Assured Follow-up of quiEscent Neovascular agE-relaTed maculaR dEgeneration by non-medical practitioners: a randomised controlled trial The FENETRE study | No |  | 2019-04-01 | 2019-07-16 | 2019-03-25 | 2019-07-16 | 2019-08-19 |  |  |  |  | Y | [6 empty] | Sponsor
19/NE/0217 | 262904 | Transcutaneous vagal nerve stimulation to reduce Ileus: A feasibility study (TRANSIT) | No |  | 2019-04-15 | 2019-07-15 | 2019-07-02 | 2019-07-15 | 2019-08-13 |  |  |  |  | Y | [6 empty] | Sponsor
19/YH/0026 | 256695 | A first in human, double-blind, placebo-controlled, multicentre Phase I/II study to evaluate the safety, tolerability and immune modulatory effects of MRx-4DP0004 (a lyophilised formulation of Bifidobacterium breve proprietary strain of 4D Pharma Research) in participants taking long-term control medication for their asthma | No |  | 2019-04-25 | 2019-06-12 | 2019-04-09 | 2019-10-07 | 2019-10-08 |  |  |  |  | Y | [6 empty] | Sponsor
19/EM/0142 | 260307 | A PHASE 3, MULTICENTER, RANDOMIZED, DOUBLE-BLIND, PLACEBO-CONTROLLED, ACTIVE REFERENCE (ADALIMUMAB) STUDY EVALUATING THE EFFICACY AND SAFETY OF BIMEKIZUMAB IN THE TREATMENT OF SUBJECTS WITH ACTIVE PSORIATIC ARTHRITIS | No |  | 2019-06-06 | 2019-08-05 | 2019-08-01 | 2019-10-04 | 2019-10-08 |  | Y | [6 empty] | Y |  |  | Both
19/EM/0141 | 260308 | A multicenter, phase 3, randomized, double-blind, placebo-controlled study evaluating the efficacy and safety of bimekizumab in the treatment of subjects with active psoriatic arthritis | No |  | 2019-06-06 | 2019-08-05 | 2019-07-31 | 2019-10-04 | 2019-10-08 |  | Y | [6 empty] | Y |  |  | Both
18/EM/0310 | 239782 | C-Stich2: Emergency Cervical Cerclage to Prevent Miscarriage and Preterm Birth: a Randomised Controlled Trial | No |  | 2019-03-08 | 2019-08-13 | 2018-11-16 | 2019-08-13 | 2019-09-02 | 2019-09-09
19/YH/0015 | 255446 | Beta Blockers or placebo for primary prophylaxis of oesophageal varices (BOPPP Trial). A blinded, multi-centre, clinical effectiveness and cost-effectiveness randomised controlled trial | No |  | 2019-02-07 | 2019-06-03 | 2019-04-24 | 2019-06-03 | 2019-08-28 | 2019-09-23 | Y |  |  | Y |  |  |  | Y |  |  | Both